## Sheet1 (hidden)
Level 1 Code | Level 1 Name | Level 2 Code | Level 2 Name | BPF Name | PIC
| (Process Name) |  | (Business Pattern Name)
1 | Budgeting | 1 | Determination of Asset Standard Price and Residual Value | 01 - 01 Budgeting - Determination of Asset Standard Price and Residual Value | Alfian
1 | Budgeting | 2 | Service & Sparepart Budgeting per Asset | 01 - 02 Budgeting - Service & Sparepart Budgeting per Asset | Alfian
2 | Marketing | 1 | Application Preparation | 02 - 01 Marketing - Application Preparation | Alfian
2 | Marketing | 2 | Agreement Preparation | 02 - 02 Marketing - Agreement Preparation | Alfian
2 | Marketing | 3 | Agreement Termination | 02 - 03 Marketing - Agreement Termination | Alfian
2 | Marketing | 4 | Agreement Extension | 02 - 04 Marketing - Agreement Extention | Alfian
Alfian
3 | Asset Management | 1 | Rental Unit | 03 - 01 Asset Management - Rental Unit | Alfian
3 | Asset Management | 2 | Asset Purchasing | 03 - 02 Asset Management - Asset Purchasing | Ninik
3 | Asset Management | 3 | SPAF Validation and Claim | 03 - 03 Asset Management - SPAF Validation and Claim | Alfian
3 | Asset Management | 4 | Asset Allocation | 03-04 Asset Management - Asset Allocation | Ninik
3 | Asset Management | 5 | Asset Delivery & Taking Up | 03 - 05 Asset Management - Asset Delivery & Taking Up | Ninik | l
3 | Asset Management | 6 | Document Receive and Release | 03 - 06 Asset Management - Document Receive and Release | Ninik
3 | Asset Management | 7 | Asset License Extension | 03 - 07 Asset Management - Asset License Extension | Ninik
3 | Asset Management | 8 | Asset Replacement | 03 - 08 Asset Management - Asset Replacement | Ninik
3 | Asset Management | 9 | Asset Monitoring | 03 - 09 Asset Management - Asset Monitoring | Ninik
3 | Asset Management | 10 | Asset Selling | 03 - 10 Asset Management - Asset Selling | Ninik
3 | Asset Management | 11 | Asset Disposal | 03 - 11 Asset Management - Asset Disposal | Ninik
4 | Asset Maintenance | 1 | Asset Service and Sparepart Replacement | 04 - 12 Asset Maintenance - Asset Service and Sparepart Replacement | Natalia
5 | Insurance Handling | 1 | Insurance Request | 05 - 01 Insurance Handling - Insurance Request | Sabilla
5 | Insurance Handling | 2 | Insurance Claim | 05 - 02 Insurance Handling - Insurance Claim | Sabilla
5 | Insurance Handling | 3 | Insuranse Amendment | 05 - 03 Insurance Handling - Insuranse Amendment | Sabilla
6 | Finance | 1 | Asset Disbursement | 06 - 01 Finance - Asset Disbursement | Natalia
6 | Finance | 2 | Prepare Rental Invoice/ Billing | 06 - 02 Finance - Prepare Rental Invoice/ Billing | Natalia
6 | Finance | 3 | Rental Payment Receive | 06 - 03 Finance - Rental Payment Receive | Natalia
6 | Finance | 4 | Other Disburse | 06 - 04 Finance - Other Disburse | Natalia
6 | Finance | 5 | Other Receive | 06 - 05 Finance - Other Receive | Natalia
6 | Finance | 6 | Bank Account Reconciliation | 06 - 06 Finance - Bank Account Reconciliation | Natalia
6 | Finance | 7 | End of Day and End of Month Process | 06 - 07 Finance - End of Day and End of Month Process | Natalia
7 | Collection | 1 | Rental Payment Reminder | 07 - 01 Collection - Rental Payment Reminder | Sabilla
7 | Collection | 2 | Overdue Maintenance | 07 - 02 Collection - Overdue Maintenance | Sabilla
7 | Collection | 3 | Waive of Penalty | 07 - 03 Collection - Waive of Penalty | Sabilla
7 | Collection | 4 | Taxation | 07 - 04 Collection - Taxation | Sabilla
7 | Collection | 5 | Write Off | 07 - 05 Collection - Write Off | Sabilla
8 | Master Data | 1 | Master Data Management | 08 - 01 Master Data - Master Data Management

## Test Case&Step
Project Name | iFinancing System Implementation
Document Name | DOC02-02 - Replace - Document Temporary |  | Business Line | Document | Tested by |  | Version | 1
|  | 0 | 4 |  |  | 4 | 0
Test Data | System Date | Execution Date | Step # | Step Description | Expected Result | Status | Re-Test Date | Notes
|  |  | 1 | - Pilih module Document - Pilih Transaction - Pilih Temporary Request - Cari datanya --> checklist --> Print Surat Tagih --> Proceed | 1. Pastikan semua field dan button berfungsi dengan baik 2. Pastikan jika tidak mengisi field mandatory menampilkan validasi 3. Pastikan setelah Proceed dari Temporery Request data masuk ke Temporary | OK
|  |  | 2 | Temporary - cari datanya --> klik Action | 1. Pastikan semua field dan button berfungsi dengan baik | OK
|  |  | 3 | - lengkapi field - Pilih Replace - Pilih save - Post | 1. Pastikan jika tidak mengisi field mandatory menampilkan validasi 2. Pastikan setelah Post dari Temporary data masuk ke Document Main dengan Status: On Hand, Locker Position: Outlocker | OK
|  |  | 4 | - Pilih Store - Add - lengkapi mandatory data - Save - Add document List - Post | 1. Pastikan jika tidak mengisi field mandatory menampilkan validasi 2. Pastikan setelah Post dari Temporary data masuk ke Document Main dengan Status: On Hand, Locker Position: InLocker | OK |  | 229 (Closed)

## DP-06
Data Pattern (DP)
NO | Quotation | [14 empty] | Application |  |  | Purchase Unit |  |  |  |  | GRN (Good Receiving) | Delivery |  | Insurance |  | Generate Invoice |  |  |  |  | Maintenance |  |  |  |  | Maturity |  | Reimbursement |  |  | Asset Selling |  |  | Collection
# | Rental Amount | Rent to Own | TOP | Asset Type | Condition | Unit Name | Merk | Unit Price | Asset | Karoseri | Karoseri Price | Mobilization | Mobilization Price | SPAF | Subvention | Approver | Kontrak Induk | Unit Alokasi (Stock) | Number of Supplier | Jumlah Unit | Asset From | Asset Purpose | With quotation | Multi Receiving Date (from dealer) | Delivery Type | Split PO | Endorsement | All Risk | PPH Treatment | Type Invoice | Due Date | Unit Breakdown | Payment Receive | Maintenance Handling | Budget Maintenance | Replacement | Service Type | Maintenance By | Maturity | Additional Period | Maintenance | Mobilization | Extension Document | Sell Type | ET/Non-ET | Sell Settelment | Late Payment Document Generating Type | Payment reminder and treatment
6 |  |  |  | Vehicle | New | Mitsubishi Xpander | Mitsubishi |  | Single Asset | Without Karoseri | [8 empty] | Single Supplier | 1 | Buy | Internal | Without Quotation | Same Asset | [5 empty] | Same Asset |  |  |  | Maintenance |  |  | Routine | Internal

## EVD_DOC02-02
Test Case ID | DOC02-01
Test Case Summary
Step # | Test Evidence | Re-Test Evidence (if found Bug/Issue)
1
2
3
4
5
6
7
8
9
10
11
13
14
15
16
17
18
19
20
21
22
36
37
38
39
41
43
44
45
46