## Sheet1 (hidden)
Level 1 Code | Level 1 Name | Level 2 Code | Level 2 Name | BPF Name | PIC
| (Process Name) |  | (Business Pattern Name)
1 | Budgeting | 1 | Determination of Asset Standard Price and Residual Value | 01 - 01 Budgeting - Determination of Asset Standard Price and Residual Value | Alfian
1 | Budgeting | 2 | Service & Sparepart Budgeting per Asset | 01 - 02 Budgeting - Service & Sparepart Budgeting per Asset | Alfian
2 | Marketing | 1 | Application Preparation | 02 - 01 Marketing - Application Preparation | Alfian
2 | Marketing | 2 | Agreement Preparation | 02 - 02 Marketing - Agreement Preparation | Alfian
2 | Marketing | 3 | Agreement Termination | 02 - 03 Marketing - Agreement Termination | Alfian
2 | Marketing | 4 | Agreement Extension | 02 - 04 Marketing - Agreement Extention | Alfian
Alfian
3 | Asset Management | 1 | Rental Unit | 03 - 01 Asset Management - Rental Unit | Alfian
3 | Asset Management | 2 | Asset Purchasing | 03 - 02 Asset Management - Asset Purchasing | Ninik
3 | Asset Management | 3 | SPAF Validation and Claim | 03 - 03 Asset Management - SPAF Validation and Claim | Alfian
3 | Asset Management | 4 | Asset Allocation | 03-04 Asset Management - Asset Allocation | Ninik
3 | Asset Management | 5 | Asset Delivery & Taking Up | 03 - 05 Asset Management - Asset Delivery & Taking Up | Ninik | l
3 | Asset Management | 6 | Document Receive and Release | 03 - 06 Asset Management - Document Receive and Release | Ninik
3 | Asset Management | 7 | Asset License Extension | 03 - 07 Asset Management - Asset License Extension | Ninik
3 | Asset Management | 8 | Asset Replacement | 03 - 08 Asset Management - Asset Replacement | Ninik
3 | Asset Management | 9 | Asset Monitoring | 03 - 09 Asset Management - Asset Monitoring | Ninik
3 | Asset Management | 10 | Asset Selling | 03 - 10 Asset Management - Asset Selling | Ninik
3 | Asset Management | 11 | Asset Disposal | 03 - 11 Asset Management - Asset Disposal | Ninik
4 | Asset Maintenance | 1 | Asset Service and Sparepart Replacement | 04 - 12 Asset Maintenance - Asset Service and Sparepart Replacement | Natalia
5 | Insurance Handling | 1 | Insurance Request | 05 - 01 Insurance Handling - Insurance Request | Sabilla
5 | Insurance Handling | 2 | Insurance Claim | 05 - 02 Insurance Handling - Insurance Claim | Sabilla
5 | Insurance Handling | 3 | Insuranse Amendment | 05 - 03 Insurance Handling - Insuranse Amendment | Sabilla
6 | Finance | 1 | Asset Disbursement | 06 - 01 Finance - Asset Disbursement | Natalia
6 | Finance | 2 | Prepare Rental Invoice/ Billing | 06 - 02 Finance - Prepare Rental Invoice/ Billing | Natalia
6 | Finance | 3 | Rental Payment Receive | 06 - 03 Finance - Rental Payment Receive | Natalia
6 | Finance | 4 | Other Disburse | 06 - 04 Finance - Other Disburse | Natalia
6 | Finance | 5 | Other Receive | 06 - 05 Finance - Other Receive | Natalia
6 | Finance | 6 | Bank Account Reconciliation | 06 - 06 Finance - Bank Account Reconciliation | Natalia
6 | Finance | 7 | End of Day and End of Month Process | 06 - 07 Finance - End of Day and End of Month Process | Natalia
7 | Collection | 1 | Rental Payment Reminder | 07 - 01 Collection - Rental Payment Reminder | Sabilla
7 | Collection | 2 | Overdue Maintenance | 07 - 02 Collection - Overdue Maintenance | Sabilla
7 | Collection | 3 | Waive of Penalty | 07 - 03 Collection - Waive of Penalty | Sabilla
7 | Collection | 4 | Taxation | 07 - 04 Collection - Taxation | Sabilla
7 | Collection | 5 | Write Off | 07 - 05 Collection - Write Off | Sabilla
8 | Master Data | 1 | Master Data Management | 08 - 01 Master Data - Master Data Management

## Test Case&Step
Project Name | iFinancing System Implementation
Document Name | DOC03-01 Lakukan Borrow Document oleh client - Ada di Locker |  | Business Line | Document | Tested by | Chris | Version | 1
|  | 2023-08-21 | 8 |  |  | 8 | 0
Test Data | System Date | Execution Date | Step # | Step Description | Expected Result | Status | Re-Test Date | Notes
| 2023-08-21 | 2023-08-21 | 1 | - Pilih module Document - Pilih Transaction - Sub Menu Retrive - add retrive | Pastikan semua field dan button berfungsi dengan baik | OK |  |  | Chris
| 2023-08-21 | 2023-08-21 | 2 | - lengkapi filed2 mandatory --> klik save | Pastikan jika tidak mengisi field mandatory menampilkan validasi | OK |  |  | Chris
| 2023-08-21 | 2023-08-21 | 3 | - add document list --> pilih document pada list - klik save ---> klik Post | 1. Pastikan semua field dan button berfungsi dengan baik 2. Pastikan jika tidak mengisi field mandatory menampilkan validasi 3. Pastikan list yang muncul pada add document retrive adalah hanya document yang= In Locker 4. Pastikan saat retrive di Post maka status di document main berubah menjadi OUT LOCKER | OK |  |  | Chris
| 2023-08-21 | 2023-08-21 | 4 | * Kemudian lakukan proses Send dengan Location Borrow Client 1. Sub Menu Send - Add send | Pastikan semua field dan button berfungsi dengan baik | OK |  |  | Chris
| 2023-08-21 | 2023-08-21 | 5 | - Lengkapi semua field mandatory --> pilih location Borrow Customer --> klik save | Pastikan jika tidak mengisi field mandatory menampilkan validasi | OK |  | issue 350 (closed) 1. tidak muncul tombol print tanda terima (setelah approved) step Document - Borrow Client 2. setelah klik tombol print tanda terima jaminan - hasil tidak muncul 502 : ready retest nomor perjanjian dan nama customer = sdh ada, a/n = seharusnya di isi sesuai nama bpkb dibawah nama chris = seharusnya kosong jabatan Pak Verdian = Dept Head (OPL Operation) | Chris
| 2023-08-21 | 2023-08-21 | 6 | - Add document list --> pilih document pada list --> Input document collateral - Klik save --> klik proceed | 1. Pastikan semua field dan button berfungsi dengan baik 2. Pastikan list yang muncul pada add document Send adalah hanya document yang status= On Hand - Out Locker 3. Pastikan setelah data di proceed dari Send masuk ke module approval | OK |  | Issue #189 (Closed) Muncul button Print setelah Approve di page Send Info setelah dilakukan Approval. Sebelum approval, dalam page Send tidak muncul button Print 182 (Closed) Perlu penambahan untuk Document Release: 1. 3 Persetujuan (Yang Menyerahkan, Yang Menerima, Menyetujui) 2. Informasi kendaraan (merk, no engine, chasis, Nomor Polisi) 239 (Closed) 503 (ready re-test) no agr = salah nama customer = beda description = kosong total agr = seharusnya 1 | Chris
| 2023-08-21 | 2023-08-21 | 7 | * Setelah di proceed data akan masuk ke module approval untuk proses approve 1. Masuk ke modul Approval - Pilih menu Transaction -> Approval Task - Cari datanya lalu klik Action | Pastikan semua field dan button berfungsi dengan baik | OK |  |  | Chris
| 2023-08-21 | 2023-08-21 | 8 | Lengkapi field lalu klik Approval - Pilih modul document --> send --> pilih branch dan status On Transit | 1. Pastikan jika tidak mengisi field mandatory menampilkan validasi 2. Pastikan setelah di approve, status di Send berubah menjadi Approve 3. Pastikan setelah di approve, di document main berubah status menjadi On Transit | OK | 2023-08-31 | Issue#183 Knowledge (Closed) | Chris

## DP-08
Data Pattern (DP)
NO | Quotation | [14 empty] | Application |  |  | Purchase Unit |  |  |  |  | GRN (Good Receiving) | Delivery |  | Insurance |  | Generate Invoice |  |  |  |  | Maintenance |  |  |  |  | Maturity |  | Reimbursement |  |  | Asset Selling |  |  | Collection
# | Rental Amount | Rent to Own | TOP | Asset Type | Condition | Unit Name | Merk | Unit Price | Asset | Karoseri | Karoseri Price | Mobilization | Mobilization Price | SPAF | Subvention | Approver | Kontrak Induk | Unit Alokasi (Stock) | Number of Supplier | Jumlah Unit | Asset From | Asset Purpose | With quotation | Multi Receiving Date (from dealer) | Delivery Type | Split PO | Endorsement | All Risk | PPH Treatment | Type Invoice | Due Date | Unit Breakdown | Payment Receive | Maintenance Handling | Budget Maintenance | Replacement | Service Type | Maintenance By | Maturity | Additional Period | Maintenance | Mobilization | Extension Document | Sell Type | ET/Non-ET | Sell Settelment | Late Payment Document Generating Type | Payment reminder and treatment
8 |  |  |  | Vehicle | New | Mitsubishi Xpander | Mitsubishi |  | Multi Asset | Without Karoseri | [8 empty] | Single Supplier | 4 | Buy | Internal | Without Quotation | Same Agreement | Partial Delivery | YES | [7 empty] | Maintenance |  |  | Routine | Internal

## EVD_DOC03-01
Test Case ID
Test Case Summary
Step # | Test Evidence | Re-Test Evidence (if found Bug/Issue)
1
2
3
4
5
6
7
8
9
10
11
13
14
15
16
17
18
19
20
21
22
36
37
38
39
41
43
44
45
46