## Sheet1 (hidden)
Level 1 Code | Level 1 Name | Level 2 Code | Level 2 Name | BPF Name | PIC
| (Process Name) |  | (Business Pattern Name)
1 | Budgeting | 1 | Determination of Asset Standard Price and Residual Value | 01 - 01 Budgeting - Determination of Asset Standard Price and Residual Value | Alfian
1 | Budgeting | 2 | Service & Sparepart Budgeting per Asset | 01 - 02 Budgeting - Service & Sparepart Budgeting per Asset | Alfian
2 | Marketing | 1 | Application Preparation | 02 - 01 Marketing - Application Preparation | Alfian
2 | Marketing | 2 | Agreement Preparation | 02 - 02 Marketing - Agreement Preparation | Alfian
2 | Marketing | 3 | Agreement Termination | 02 - 03 Marketing - Agreement Termination | Alfian
2 | Marketing | 4 | Agreement Extension | 02 - 04 Marketing - Agreement Extention | Alfian
Alfian
3 | Asset Management | 1 | Rental Unit | 03 - 01 Asset Management - Rental Unit | Alfian
3 | Asset Management | 2 | Asset Purchasing | 03 - 02 Asset Management - Asset Purchasing | Ninik
3 | Asset Management | 3 | SPAF Validation and Claim | 03 - 03 Asset Management - SPAF Validation and Claim | Alfian
3 | Asset Management | 4 | Asset Allocation | 03-04 Asset Management - Asset Allocation | Ninik
3 | Asset Management | 5 | Asset Delivery & Taking Up | 03 - 05 Asset Management - Asset Delivery & Taking Up | Ninik | l
3 | Asset Management | 6 | Document Receive and Release | 03 - 06 Asset Management - Document Receive and Release | Ninik
3 | Asset Management | 7 | Asset License Extension | 03 - 07 Asset Management - Asset License Extension | Ninik
3 | Asset Management | 8 | Asset Replacement | 03 - 08 Asset Management - Asset Replacement | Ninik
3 | Asset Management | 9 | Asset Monitoring | 03 - 09 Asset Management - Asset Monitoring | Ninik
3 | Asset Management | 10 | Asset Selling | 03 - 10 Asset Management - Asset Selling | Ninik
3 | Asset Management | 11 | Asset Disposal | 03 - 11 Asset Management - Asset Disposal | Ninik
4 | Asset Maintenance | 1 | Asset Service and Sparepart Replacement | 04 - 12 Asset Maintenance - Asset Service and Sparepart Replacement | Natalia
5 | Insurance Handling | 1 | Insurance Request | 05 - 01 Insurance Handling - Insurance Request | Sabilla
5 | Insurance Handling | 2 | Insurance Claim | 05 - 02 Insurance Handling - Insurance Claim | Sabilla
5 | Insurance Handling | 3 | Insuranse Amendment | 05 - 03 Insurance Handling - Insuranse Amendment | Sabilla
6 | Finance | 1 | Asset Disbursement | 06 - 01 Finance - Asset Disbursement | Natalia
6 | Finance | 2 | Prepare Rental Invoice/ Billing | 06 - 02 Finance - Prepare Rental Invoice/ Billing | Natalia
6 | Finance | 3 | Rental Payment Receive | 06 - 03 Finance - Rental Payment Receive | Natalia
6 | Finance | 4 | Other Disburse | 06 - 04 Finance - Other Disburse | Natalia
6 | Finance | 5 | Other Receive | 06 - 05 Finance - Other Receive | Natalia
6 | Finance | 6 | Bank Account Reconciliation | 06 - 06 Finance - Bank Account Reconciliation | Natalia
6 | Finance | 7 | End of Day and End of Month Process | 06 - 07 Finance - End of Day and End of Month Process | Natalia
7 | Collection | 1 | Rental Payment Reminder | 07 - 01 Collection - Rental Payment Reminder | Sabilla
7 | Collection | 2 | Overdue Maintenance | 07 - 02 Collection - Overdue Maintenance | Sabilla
7 | Collection | 3 | Waive of Penalty | 07 - 03 Collection - Waive of Penalty | Sabilla
7 | Collection | 4 | Taxation | 07 - 04 Collection - Taxation | Sabilla
7 | Collection | 5 | Write Off | 07 - 05 Collection - Write Off | Sabilla
8 | Master Data | 1 | Master Data Management | 08 - 01 Master Data - Master Data Management

## Test Case&Step
Project Name | iFinancing System Implementation
Document Name | UAT OPL02-19-Asset allocation |  | Business Line |  | Tested By |  | Version | 1.0
|  | 2023-09-13 | 13 |  |  | 13 | 0
Test Data | System Date | Execution Date | Step # | Step Description | Expected Result | Status | Re-Test Date | Notes
|  | 2023-09-13 | 1 | Login IFINANCING, Masuk ke modul OPL, klik menu contract lalu klik asset allocation | Semua button dan field berfungsi dengan baik. | OK
|  | 2023-09-13 | 2 | Pilih branch lalu klik action pada aplikasi yang akan diproses | layar berhasil masuk ke asset allocation info | OK
|  | 2023-09-13 | 3 | Pada Asset Allocation dapat menentukan Pembelian atau Pemilihan unit yang ready di pool. Untuk tipe Used car, maka asset otomatis sudah teralokasi. | Dapat melakukan pembelian dan pemilihan unit yang ready di pool | OK
|  | 2023-09-13 | 4 | pilih asset, klik post. | status asset akan berubah menjadi Realization | OK
Single asset, tanpa karoseri, tanpa mobilisasi |  | 2023-09-13 | 5 | Kemudian masuk ke menu Realization Request. Realization Request - select data yang ingin di Proceed -> kemudian di Proceed dan masuk ke menu realization | Setelah proceed maka akan masuk ke realization | OK
|  | 2023-09-13 | 6 | Pada Menu Realization, klik action pada aplikasi yang dipilih, lengkapi data kemudian proceed | Kontrak pelaksana dicetak | OK
|  | 2023-09-13 | 7 | Cetak kontrak pada proses realization, lakukan verification kontrak oleh Legal dan upload kontrak, lalu proceed to legal, lalu POST | Kontrak diverifikasi oleh legal. Setelah POST, data masuk ke menu handover Request di module FAM | OK
|  | 2023-09-13 | 8 | Masuk ke Modul FAM -> Pada menu Handover Request, Select data yang ingin di Proceed. | Asset aplikasi diproses untuk handover. | OK |  | Asset
|  | 2023-09-13 | 9 | Kemudian di Proceed dan masuk ke menu Handover | Handover diproses. | OK |  | Asset
|  | 2023-09-13 | 10 | Print surat jalan | Surat Jalan dicetak. | OK |  | Asset
|  | 2023-09-13 | 11 | Pada proses handover, Print BAST. | Schedule due date yang terbentuk adalah tgl BAST. BAST tercetak. | OK |  | Asset
|  | 2023-09-13 | 12 | Lengkapi tab Asset document | Tab Asset Document dilengkapi | OK |  | Asset
|  | 2023-09-13 | 13 | Lengkapi field2 di Handover Info -> Kemudian di post | Semua field berfungsi dengan baik. | OK |  | Asset

## EVD_OPL02-19
Test Case ID | 02
Test Case Summary
Step # | Test Evidence | Re-Test Evidence (if found Bug/Issue)
1
2
3
4
5
6
7
8
9
10
11
12
13