## Sheet1 (hidden)
Level 1 Code | Level 1 Name | Level 2 Code | Level 2 Name | BPF Name | PIC
| (Process Name) |  | (Business Pattern Name)
1 | Budgeting | 1 | Determination of Asset Standard Price and Residual Value | 01 - 01 Budgeting - Determination of Asset Standard Price and Residual Value | Alfian
1 | Budgeting | 2 | Service & Sparepart Budgeting per Asset | 01 - 02 Budgeting - Service & Sparepart Budgeting per Asset | Alfian
2 | Marketing | 1 | Application Preparation | 02 - 01 Marketing - Application Preparation | Alfian
2 | Marketing | 2 | Agreement Preparation | 02 - 02 Marketing - Agreement Preparation | Alfian
2 | Marketing | 3 | Agreement Termination | 02 - 03 Marketing - Agreement Termination | Alfian
2 | Marketing | 4 | Agreement Extension | 02 - 04 Marketing - Agreement Extention | Alfian
Alfian
3 | Asset Management | 1 | Rental Unit | 03 - 01 Asset Management - Rental Unit | Alfian
3 | Asset Management | 2 | Asset Purchasing | 03 - 02 Asset Management - Asset Purchasing | Ninik
3 | Asset Management | 3 | SPAF Validation and Claim | 03 - 03 Asset Management - SPAF Validation and Claim | Alfian
3 | Asset Management | 4 | Asset Allocation | 03-04 Asset Management - Asset Allocation | Ninik
3 | Asset Management | 5 | Asset Delivery & Taking Up | 03 - 05 Asset Management - Asset Delivery & Taking Up | Ninik | l
3 | Asset Management | 6 | Document Receive and Release | 03 - 06 Asset Management - Document Receive and Release | Ninik
3 | Asset Management | 7 | Asset License Extension | 03 - 07 Asset Management - Asset License Extension | Ninik
3 | Asset Management | 8 | Asset Replacement | 03 - 08 Asset Management - Asset Replacement | Ninik
3 | Asset Management | 9 | Asset Monitoring | 03 - 09 Asset Management - Asset Monitoring | Ninik
3 | Asset Management | 10 | Asset Selling | 03 - 10 Asset Management - Asset Selling | Ninik
3 | Asset Management | 11 | Asset Disposal | 03 - 11 Asset Management - Asset Disposal | Ninik
4 | Asset Maintenance | 1 | Asset Service and Sparepart Replacement | 04 - 12 Asset Maintenance - Asset Service and Sparepart Replacement | Natalia
5 | Insurance Handling | 1 | Insurance Request | 05 - 01 Insurance Handling - Insurance Request | Sabilla
5 | Insurance Handling | 2 | Insurance Claim | 05 - 02 Insurance Handling - Insurance Claim | Sabilla
5 | Insurance Handling | 3 | Insuranse Amendment | 05 - 03 Insurance Handling - Insuranse Amendment | Sabilla
6 | Finance | 1 | Asset Disbursement | 06 - 01 Finance - Asset Disbursement | Natalia
6 | Finance | 2 | Prepare Rental Invoice/ Billing | 06 - 02 Finance - Prepare Rental Invoice/ Billing | Natalia
6 | Finance | 3 | Rental Payment Receive | 06 - 03 Finance - Rental Payment Receive | Natalia
6 | Finance | 4 | Other Disburse | 06 - 04 Finance - Other Disburse | Natalia
6 | Finance | 5 | Other Receive | 06 - 05 Finance - Other Receive | Natalia
6 | Finance | 6 | Bank Account Reconciliation | 06 - 06 Finance - Bank Account Reconciliation | Natalia
6 | Finance | 7 | End of Day and End of Month Process | 06 - 07 Finance - End of Day and End of Month Process | Natalia
7 | Collection | 1 | Rental Payment Reminder | 07 - 01 Collection - Rental Payment Reminder | Sabilla
7 | Collection | 2 | Overdue Maintenance | 07 - 02 Collection - Overdue Maintenance | Sabilla
7 | Collection | 3 | Waive of Penalty | 07 - 03 Collection - Waive of Penalty | Sabilla
7 | Collection | 4 | Taxation | 07 - 04 Collection - Taxation | Sabilla
7 | Collection | 5 | Write Off | 07 - 05 Collection - Write Off | Sabilla
8 | Master Data | 1 | Master Data Management | 08 - 01 Master Data - Master Data Management

## Test Case&Step
Project Name | iFinancing System Implementation
Document Name | UAT OPL03-27-Generate Billing Otomatis |  | Business Line |  | Tested By |  | Version | 1.0
|  | 2023-09-21 | 13 |  |  | 13 | 0
Test Data | System Date | Execution Date | Step # | Step Description | Expected Result | Status | Re-Test Date | Notes
|  | 2023-09-21 | 1 | Masuk ke modul OPL-> Billing-> Generate Invoive. - Klik action pada invoice yang akan diproses. - Klik Post | 1. Semua list sesuai schedule yang dipost akan masuk ke sub menu Invoice. 2. List yang muncul di Generate invoice adalah tagihan yang h-2 jatuh tempo. 3. Jika h-2 jatuh temponya hari libur nasional/sabtu minggu maka muncul di list dihari kerja sebelum hari libur tersebut. 4. Status invoice pada invoice list menjadi NEW | OK |  | Proses Billing dapat dilakukan hanya setelah kontrak Go Live
|  | 2023-09-21 | 2 | Masuk ke menu Taxation-> Faktur No Allocation. - klik Add pada sub-menu FAKTUR NO. ALLOCATION. - lengkapi data - klik save | Semua field dan button berfungsi dengan baik | OK
|  | 2023-09-21 | 3 | Pada Faktur No. Allocation Info Detail List, - klik refresh untuk memunculkan data invoice | Data invoice tersedia pada Faktur No. Allocation Info Detail List. | OK
|  | 2023-09-21 | 4 | Klik Proceed, print pajak, lalu POST | Faktur pajak dicetak. Faktur telah dialokasi | OK
|  | 2023-09-21 | 5 | Masuk ke menu Billing-> Invoice. - Klik action di data yang ingin di cetak invoice | Button berfungsi dengan baik | OK
|  | 2023-09-21 | 6 | - Print Invoice - Print Kwitansi - Klik POST | Invoice dicetak. Data masuk ke Delivery | OK
|  | 2023-09-21 | 7 | Masuk ke sub menu Delivery Request. - Select invoice yang ingin dikirim ke customer. - Proceed | Data yang di select di Delivery Request masuk ke Delivery | OK
|  | 2023-09-21 | 8 | Masuk ke sub menu Delivery. - klik action - Lengkapi field - klik Proceed | Detail ditampilkan. Field2 yang mandatory ketika tidak diisi terkena validasi | OK
|  | 2023-09-21 | 9 | Pada Invoice List, - klik action - upload file - lengkapi semua field - klik save | File diupload | OK |  | Setelah Invoice ter Deliver maka customer sudah bisa melakukan pembayaran.
|  | 2023-09-21 | 10 | Masuk ke Modul Finance-> Chasier-> Chasier Open. - Cek apakah sudah ada open kasir. - Jika belum open kasir, maka pada menu CHASIER OPEN, cek status yang sudah open per cabang terlebih dahulu | 1. Pastikan data masuk ke modul finance setelah customer melakukan pembayaran. 2. Data yang masuk ke Finance hanya saat invoice sudah terdelivery. | OK |  | Memastikan apakah sudah chasier open (bisa 1 kasir open untuk semua cabang) untuk melakukan chasier received.
|  | 2023-09-21 | 11 | Masuk ke sub menu Cashier Received. - Pilih Bank - Pilih Branch - Select data yang akan diproses - klik Proceed to cashier | Data tersedia di cashier received request list, setelah proceed Data masuk ke sub menu Cashier Trasaction | OK
|  | 2023-09-21 | 12 | Masuk ke sub menu Chasier Transaction. - Pilih Bank - Pilih Branch - Select data yang akan diproses - klik action | Field2 yang mandatory ketika tidak diisi terkena validasi | OK
|  | 2023-09-21 | 13 | Lengkapi semua field lalu POST | Billing menjadi Paid saat sudah di post di Finance dan Jurnal terbentuk | OK

## EVD_OPL03-27
Test Case ID | 01
Test Case Summary | Lakukan cetak invoice dari generate billing otomatis sampai dengan proses pembayaran invoice oleh customer - 0001555/4/00/09/2023
Step # | Test Evidence | Re-Test Evidence (if found Bug/Issue)
1
2
3
4
5
6
7
8
9
10
11
13