## Sheet1 (hidden)
Level 1 Code | Level 1 Name | Level 2 Code | Level 2 Name | BPF Name | PIC
| (Process Name) |  | (Business Pattern Name)
1 | Budgeting | 1 | Determination of Asset Standard Price and Residual Value | 01 - 01 Budgeting - Determination of Asset Standard Price and Residual Value | Alfian
1 | Budgeting | 2 | Service & Sparepart Budgeting per Asset | 01 - 02 Budgeting - Service & Sparepart Budgeting per Asset | Alfian
2 | Marketing | 1 | Application Preparation | 02 - 01 Marketing - Application Preparation | Alfian
2 | Marketing | 2 | Agreement Preparation | 02 - 02 Marketing - Agreement Preparation | Alfian
2 | Marketing | 3 | Agreement Termination | 02 - 03 Marketing - Agreement Termination | Alfian
2 | Marketing | 4 | Agreement Extension | 02 - 04 Marketing - Agreement Extention | Alfian
Alfian
3 | Asset Management | 1 | Rental Unit | 03 - 01 Asset Management - Rental Unit | Alfian
3 | Asset Management | 2 | Asset Purchasing | 03 - 02 Asset Management - Asset Purchasing | Ninik
3 | Asset Management | 3 | SPAF Validation and Claim | 03 - 03 Asset Management - SPAF Validation and Claim | Alfian
3 | Asset Management | 4 | Asset Allocation | 03-04 Asset Management - Asset Allocation | Ninik
3 | Asset Management | 5 | Asset Delivery & Taking Up | 03 - 05 Asset Management - Asset Delivery & Taking Up | Ninik | l
3 | Asset Management | 6 | Document Receive and Release | 03 - 06 Asset Management - Document Receive and Release | Ninik
3 | Asset Management | 7 | Asset License Extension | 03 - 07 Asset Management - Asset License Extension | Ninik
3 | Asset Management | 8 | Asset Replacement | 03 - 08 Asset Management - Asset Replacement | Ninik
3 | Asset Management | 9 | Asset Monitoring | 03 - 09 Asset Management - Asset Monitoring | Ninik
3 | Asset Management | 10 | Asset Selling | 03 - 10 Asset Management - Asset Selling | Ninik
3 | Asset Management | 11 | Asset Disposal | 03 - 11 Asset Management - Asset Disposal | Ninik
4 | Asset Maintenance | 1 | Asset Service and Sparepart Replacement | 04 - 12 Asset Maintenance - Asset Service and Sparepart Replacement | Natalia
5 | Insurance Handling | 1 | Insurance Request | 05 - 01 Insurance Handling - Insurance Request | Sabilla
5 | Insurance Handling | 2 | Insurance Claim | 05 - 02 Insurance Handling - Insurance Claim | Sabilla
5 | Insurance Handling | 3 | Insuranse Amendment | 05 - 03 Insurance Handling - Insuranse Amendment | Sabilla
6 | Finance | 1 | Asset Disbursement | 06 - 01 Finance - Asset Disbursement | Natalia
6 | Finance | 2 | Prepare Rental Invoice/ Billing | 06 - 02 Finance - Prepare Rental Invoice/ Billing | Natalia
6 | Finance | 3 | Rental Payment Receive | 06 - 03 Finance - Rental Payment Receive | Natalia
6 | Finance | 4 | Other Disburse | 06 - 04 Finance - Other Disburse | Natalia
6 | Finance | 5 | Other Receive | 06 - 05 Finance - Other Receive | Natalia
6 | Finance | 6 | Bank Account Reconciliation | 06 - 06 Finance - Bank Account Reconciliation | Natalia
6 | Finance | 7 | End of Day and End of Month Process | 06 - 07 Finance - End of Day and End of Month Process | Natalia
7 | Collection | 1 | Rental Payment Reminder | 07 - 01 Collection - Rental Payment Reminder | Sabilla
7 | Collection | 2 | Overdue Maintenance | 07 - 02 Collection - Overdue Maintenance | Sabilla
7 | Collection | 3 | Waive of Penalty | 07 - 03 Collection - Waive of Penalty | Sabilla
7 | Collection | 4 | Taxation | 07 - 04 Collection - Taxation | Sabilla
7 | Collection | 5 | Write Off | 07 - 05 Collection - Write Off | Sabilla
8 | Master Data | 1 | Master Data Management | 08 - 01 Master Data - Master Data Management

## Test Case&Step
Project Name | iFinancing System Implementation
Document Name | OPL09-01-Replacement |  | Business Line |  | Tested By |  | Version | 1.0
|  | 0 | 27 |  |  | 0 | 0
Test Data | System Date | Execution Date | Step # | Step Description | Expected Result | Status | Re-Test Date | Notes
|  |  | 1 | - Pilih Module Operating Lease - Pilih Account Maintenance - Entry Asset Replacement | Field dan button berfungsi dengan baik
|  |  | 2 | Pilih field: - Date - Branch - Remark - Agreement# | Field dan button berfungsi dengan baik
|  |  | 3 | Lengkapi Asset Detail List lalu Proceed kemudian Post dan akan masuk modul Approval: - Add - Action: Select - Pilih Old Asset - Action: Select - Pilih New Asset No - Pilih reason - Estimate Return Date - Remark - Save - Proceed | - Field dan button berfungsi dengan baik - Sebelum melengkapi Asset Detail List menampilkan validasi - Save succesfull after input Asset Detail List
|  |  | 4 | - Pilih Module Operating Lease - Pilih Account Maintenance - Entry Asset Replacement - Pilih drop down Status: On Process - Pilih Branch - Pilih Status - Pilih Action - Pilih Post
|  |  | 5 | Masuk ke modul Approval: - Pilih menu Transaction - Pilih Approval Task | Masuk ke Approval Task
|  |  | 6 | Cari datanya lalu klik Action | Field dan button berfungsi dengan baik
|  |  | 7 | Lengkapi field: - Remark - Klik Approve | Setelah di Approve maka masuk ke modul AMS dan pada Asset Replacement List statusnya menjadi Post
|  |  | 8 | Masuk ke modul AMS: - Pilih menu Transaction - Pilih Handover Request - Pilih Branch - Pilih Status | Masuk ke Handover Request List
|  |  | 9 | Pada Handover Request List; - Cari datanya type Replace In dan Out - Checklist lalu klik Proceed maka akan masuk ke Handover | Setelah Proceed dari Handover Request List masuk ke Handover List
|  |  | 10 | Pada Handover Pilih: - Pilih Branch - Pilih Status - Type - Pilih Action | Field dan button berfungsi dengan baik
|  |  | 11 | Print BAST | BAST dicetak
|  |  | 12 | Lengkapi semua field kemudian Post - Process Status - Plan Date - Unit Condition - Remark** - Post | - Field dan button berfungsi dengan baik - Post successfully |  |  | *dapat memilih sesuai kebutuhan **Auto filled tapi dapat di edit - Handover Date must be less than System Date
|  |  | 13 | - Pilih Module Operating Lease - Pilih Account Maintenance - Pilih Asset Replacement - Pilih Branch - Pilih Status - Pilih Action - Cek di Asset Detail List, status Out | Setelah di Post dari Handover pada Asset Replacement -> Asset Detail List status In Out warnanya berubah ketika sudah Handover
|  |  | 14 | Process Old Asset to In: - Pilih Fixed Asset Management - Pilih Handover Request - Pilih Branch - Pilih Status - Pilih Checklist Asset yang sesuai - Pilih Proceed | - Field dan button berfungsi dengan baik - Proceed successfully
|  |  | 15 | Masuk ke modul AMS: - Pilih menu Transaction - Pilih Handover - Pilih Branch - Pilih Status - Check Type - Pilih Action | - Field dan button berfungsi dengan baik
|  |  | 16 | Lengkapi semua field kemudian Post - Process Status - Plan Date - Unit Condition - Remark** | - Field dan button berfungsi dengan baik - Proceed successfully
|  |  | 17 | Print BAST | BAST dicetak
|  |  | 18 | - Post handover info | - Post successfully
|  |  | 19 | - Pilih Module Operating Lease - Pilih Account Maintenance - Pilih Asset Replacement - Pilih Branch - Pilih Status - Pilih Action - Cek di Asset Detail List, Old Asset, status In | Setelah di Post dari Handover pada Asset Replacement -> Asset Detail List status In Out warnanya berubah ketika sudah Handover
|  |  | 20 | Untuk return asset, pada Asset Replacement List cari datanya yang status nya Post kemudian klik Action | Field dan button berfungsi dengan baik
|  |  | 21 | Pada Asset Replacement Info klik Return Asset dan akan masuk ke modul AMS | Masuk ke modul AMS dan pada Asset Replacement List statusnya menjadi Post
|  |  | 22 | Pada modul AMS, pilih menu Transaction | Masuk ke Handover Request List
|  |  | 23 | Pada Handover Request List cari datanya type Return In dan Out kemudian checklist lalu klik Proceed | Setelah Proceed dari Handover Request List masuk ke Handover List
|  |  | 24 | Pada Handover Info cari datanya type Return In dan Out kemudian klik Action. | Field dan button berfungsi dengan baik
|  |  | 25 | Print BAST | BAST dicetak
|  |  | 26 | Lengkapi semua field kemudian Post - Return In | Setelah di Post dari Handover pada Asset Replacement -> Asset Detail List status In Out warnanya berubah ketika sudah Handover
|  |  | 27 | Lengkapi semua field kemudian Post - - Return Out | Setelah di Post dari Handover pada Asset Replacement -> Asset Detail List status In Out warnanya berubah ketika sudah Handover

## DP-09
Data Pattern (DP)
NO | Quotation | [14 empty] | Application |  |  | Purchase Unit |  |  |  |  | GRN (Good Receiving) | Delivery |  | Insurance |  | Generate Invoice |  |  |  |  | Maintenance |  |  |  |  | Maturity |  | Reimbursement |  |  | Asset Selling |  |  | Collection
# | Rental Amount | Rent to Own | TOP | Asset Type | Condition | Unit Name | Merk | Unit Price | Asset | Karoseri | Karoseri Price | Mobilization | Mobilization Price | SPAF | Subvention | Approver | Kontrak Induk | Unit Alokasi (Stock) | Number of Supplier | Jumlah Unit | Asset From | Asset Purpose | With quotation | Multi Receiving Date (from dealer) | Delivery Type | Split PO | Endorsement | All Risk | PPH Treatment | Type Invoice | Due Date | Unit Breakdown | Payment Receive | Maintenance Handling | Budget Maintenance | Replacement | Service Type | Maintenance By | Maturity | Additional Period | Maintenance | Mobilization | Extension Document | Sell Type | ET/Non-ET | Sell Settelment | Late Payment Document Generating Type | Payment reminder and treatment
9 |  | Non-COP | 30 Hari | Vehicle | New | Honda CRV Turbo Prestige | Non-Mitsubishi | Rp250,000,000.00 | Multi Asset | Without Karoseri | Rp- | Mobilization | Rp11,000,000.00 | NO | NO | 3% | Pilih Kontrak Baru | NO | Single Supplier | 2 | Buy | Lease | With quotation | Same Asset | Partial Delivery | YES | Termination | Tanpa perluasan | Non-WAPU | Same Asset | Due Date Berbeda | Not Breakdown | Rental Payment Receive | Not Maintenance | Rp- | Rp- | N/A | N/A | Continue Rental | 2 Months | N/A | Reimbursement | Reimbursement | COP | Non-ET | N/A | Per Asset | SP-1

## EVD_OPL 09-01
Test Case ID | 01
Test Case Summary | Lakukan replacement asset - Replacment type nya temporary
Step # | Test Evidence | Re-Test Evidence (if found Bug/Issue)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27