## Sheet1 (hidden)
Level 1 Code | Level 1 Name | Level 2 Code | Level 2 Name | BPF Name | PIC
| (Process Name) |  | (Business Pattern Name)
1 | Budgeting | 1 | Determination of Asset Standard Price and Residual Value | 01 - 01 Budgeting - Determination of Asset Standard Price and Residual Value | Alfian
1 | Budgeting | 2 | Service & Sparepart Budgeting per Asset | 01 - 02 Budgeting - Service & Sparepart Budgeting per Asset | Alfian
2 | Marketing | 1 | Application Preparation | 02 - 01 Marketing - Application Preparation | Alfian
2 | Marketing | 2 | Agreement Preparation | 02 - 02 Marketing - Agreement Preparation | Alfian
2 | Marketing | 3 | Agreement Termination | 02 - 03 Marketing - Agreement Termination | Alfian
2 | Marketing | 4 | Agreement Extension | 02 - 04 Marketing - Agreement Extention | Alfian
Alfian
3 | Asset Management | 1 | Rental Unit | 03 - 01 Asset Management - Rental Unit | Alfian
3 | Asset Management | 2 | Asset Purchasing | 03 - 02 Asset Management - Asset Purchasing | Ninik
3 | Asset Management | 3 | SPAF Validation and Claim | 03 - 03 Asset Management - SPAF Validation and Claim | Alfian
3 | Asset Management | 4 | Asset Allocation | 03-04 Asset Management - Asset Allocation | Ninik
3 | Asset Management | 5 | Asset Delivery & Taking Up | 03 - 05 Asset Management - Asset Delivery & Taking Up | Ninik | l
3 | Asset Management | 6 | Document Receive and Release | 03 - 06 Asset Management - Document Receive and Release | Ninik
3 | Asset Management | 7 | Asset License Extension | 03 - 07 Asset Management - Asset License Extension | Ninik
3 | Asset Management | 8 | Asset Replacement | 03 - 08 Asset Management - Asset Replacement | Ninik
3 | Asset Management | 9 | Asset Monitoring | 03 - 09 Asset Management - Asset Monitoring | Ninik
3 | Asset Management | 10 | Asset Selling | 03 - 10 Asset Management - Asset Selling | Ninik
3 | Asset Management | 11 | Asset Disposal | 03 - 11 Asset Management - Asset Disposal | Ninik
4 | Asset Maintenance | 1 | Asset Service and Sparepart Replacement | 04 - 12 Asset Maintenance - Asset Service and Sparepart Replacement | Natalia
5 | Insurance Handling | 1 | Insurance Request | 05 - 01 Insurance Handling - Insurance Request | Sabilla
5 | Insurance Handling | 2 | Insurance Claim | 05 - 02 Insurance Handling - Insurance Claim | Sabilla
5 | Insurance Handling | 3 | Insuranse Amendment | 05 - 03 Insurance Handling - Insuranse Amendment | Sabilla
6 | Finance | 1 | Asset Disbursement | 06 - 01 Finance - Asset Disbursement | Natalia
6 | Finance | 2 | Prepare Rental Invoice/ Billing | 06 - 02 Finance - Prepare Rental Invoice/ Billing | Natalia
6 | Finance | 3 | Rental Payment Receive | 06 - 03 Finance - Rental Payment Receive | Natalia
6 | Finance | 4 | Other Disburse | 06 - 04 Finance - Other Disburse | Natalia
6 | Finance | 5 | Other Receive | 06 - 05 Finance - Other Receive | Natalia
6 | Finance | 6 | Bank Account Reconciliation | 06 - 06 Finance - Bank Account Reconciliation | Natalia
6 | Finance | 7 | End of Day and End of Month Process | 06 - 07 Finance - End of Day and End of Month Process | Natalia
7 | Collection | 1 | Rental Payment Reminder | 07 - 01 Collection - Rental Payment Reminder | Sabilla
7 | Collection | 2 | Overdue Maintenance | 07 - 02 Collection - Overdue Maintenance | Sabilla
7 | Collection | 3 | Waive of Penalty | 07 - 03 Collection - Waive of Penalty | Sabilla
7 | Collection | 4 | Taxation | 07 - 04 Collection - Taxation | Sabilla
7 | Collection | 5 | Write Off | 07 - 05 Collection - Write Off | Sabilla
8 | Master Data | 1 | Master Data Management | 08 - 01 Master Data - Master Data Management

## Test Case&Step
Project Name | iFinancing System Implementation
Document Name | TC OPL12-01 Write off |  | Business Line |  | Tested By | Gina, Della, | Version | 1.0
|  | 0 | 6 |  |  | 6 | 0
Test Data | System Date | Execution Date | Step # | Step Description | Expected Result | Status | Re-Test Date | Notes
Process WO candidate. Menggunakan aplikasi hasil data migrasi yang sesuai dengan data pattern | 2023-09-22 |  | 1 | Pada Write Off Candidate cari data yang akan dilakukan WO kemudian Proceed '-Operating lease -account Management -Write off -Add -branch -agreement no -Proceed | - Pastikan field dan button berfungsi dengan baik. - Pastikan yang masuk ke List WO Candidate sesuai dengan parameter - Pastikan setelah Proceed dari WO Candidate masuk ke WO dengan status Hold | OK
| 2023-09-22 |  | 2 | Pada WO klik Action dan lengkapi field kemudian Proceed maka akan masuk ke modul Approval '-approval -approval task -search -action -approve | Pastikan setelah dilakukan Proceed dari WO masuk ke modul Approval | OK
| 2023-09-22 |  | 3 | Masuk ke Modul Approval dan lakukan Approve | - Pastikan setelah dilakukan Approve kontrak menjadi Terminate WO - Pastikan data customer WO akan sync ke LOS | OK
Process entry WO manual | 2023-09-22 |  | 4 | Entry WO dan lengkapi field kemudian Proceed maka akan masuk ke modul Approval '-Operating lease -account Management -Write off - add -date -branch -agreement No -Save -proceed | - Pastikan field dan button berfungsi dengan baik - Pastikan setelah dilakukan Proceed dari WO masuk ke modul Approval | OK
| 2023-09-22 |  | 5 | Masuk ke Modul Approval dan lakukan Approve -home dashboard -approval -approval task -branch -find req no -action approve | Pastikan data dapat di Approve pada modul Approval | OK |  | issue 483: user : febi (coll) Issue gagal validasi client yang bad.
| 2023-09-22 |  | 6 | Kontrak Menjadi Terminate WO '-Operating lease -account Management -inquiry -Agreement -branch | Pastikan setelah dilakukan Approve kontrak menjadi Terminate WO | OK

## DP-12
| NO | Quotation | [17 empty] | Purchase Unit |  |  |  |  | GRN (Good Receiving) | Delivery |  |  |  | Generate Invoice |  |  |  |  | Maintenance |  |  |  |  | Maturity |  | Reimbursement |  |  | Asset Selling |  |  | Collection
| # | Rental Amount | Purchase Requirement After Lease | TOP | Asset Type | Condition | Unit Name | Merk | Unit Price | Asset | Karoseri/Aksesoris | Karoseri Price | Mobilization | Mobilization Price | SPAF | Subvention | Subvention Price | Kontrak Induk | Unit Alokasi (Stock) | Number of Supplier | Jumlah Unit | Asset From | Facility | With quotation | Multi Receiving Date (from dealer) | Delivery Type | Split PO | Endorsement | Type | PPH Treatment | Type Invoice | Due Date | Unit Breakdown | Payment Receive | Maintenance Handling | Budget Maintenance | Replacement | Service Type | Maintenance By | Maturity | Additional Period | Maintenance | Mobilization | Extension Document | Sell Type | ET/Non-ET | Sell Settelment | Late Payment Document Generating Type | Payment reminder and treatment
APP-09 | 12 |  | Non-COP | 30 Hari | Vehicle | New | Honda CRV Turbo Prestige | Non-Mitsubishi | Rp250,000,000.00 | Multi Asset | Without Karoseri | Rp- | Mobilization | Rp11,000,000.00 | NO | Without Subvention | NO | Pilih Kontrak Baru | NO | Multi supplier | 1 | Buy | Lease | With quotation | Same Asset | Partial Delivery | YES | Claim | Dengan perluasan | WAPU | Same Asset | Due Date Berbeda | Breakdown | Rental Payment Receive | Not Maintenance | Rp- | Rp1,000,000.00 | N/A | N/A | Stop | N/A | N/A | Reimbursement | Reimbursement | Direct (Mocil) | N/A | Sold | Per Asset | SKT

## EVD_OPL 12-01
Test Case ID
Test Case Summary | Lakukan WO Candidate dan entry WO manual
Step # | Test Evidence | Re-Test Evidence (if found Bug/Issue)
1
2
3
4
5
6
7
8
9
10
11
13
14
15
16
17
18
19
20
21
22
36
37
38
39
41
43
44
45
46

## EVD_OPL 12-01 (GINA)
Test Case ID
Test Case Summary | Lakukan WO Candidate dan entry WO manual
Step # | Test Evidence | Re-Test Evidence (if found Bug/Issue)
1
2
3
4
5
6
7
8
9
10
11
13
14
15
16
17
18
19
20
21
22
36
37
38
39
41
43
44
45
46

## EVD_OPL 12-01 (DELLA)
Test Case ID
Test Case Summary | Lakukan WO Candidate dan entry WO manual
Step # | Test Evidence | Re-Test Evidence (if found Bug/Issue)
1
2
3
4
5
6
7
8
9
10
11
13
14
15
16
17
18
19
20
21
22
36
37
38
39
41
43
44
45
46